## Slide 2
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
LAPORAN KEMAJUAN INISIATIF BAHARU
BIL. 11
INISIATIF
JABATAN BERTANGGUNGJAWAB
STATUS SEHINGGA 21 JUN 2022
PENDIGITALAN
Jabatan Teknologi Maklumat dan Pengurusan Ilmu
Penambahbaikan sistem APEL berdasarkan maklumbalas dari MQA dan dijangka siap pada minggu pertama July 2022 (status: 90%).
Tempoh pembangunan sistem RPEL dijangka selama 3 bulan bermula July- Sept 2022.
Pembangunan modul kemasukan baharu sistem Admission PUPW pada bulan Jan-Mac 2022 (status: 100%)
Pembangunan modul saringan baharu sistem Admission PUPW pada bulan Apr-Jun 2022 (status: 70%)
Transisi pembangunan dan peralihan sistem MIS HR kepada LARAVEL dijangka bermula pada July-Dec 2022
Pembelian Microserver bagi menggantikan server Biztrak dan kegunaan sistem-sistem UMPA. Digunakan juga sebagai server development for system testing.
Unit Penyelenggaraan Sistem

## Slide 3
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
LAPORAN KEMAJUAN INISIATIF BAHARU
BIL. 11
INISIATIF
JABATAN BERTANGGUNGJAWAB
STATUS SEHINGGA 21 JUN 2022
PENDIGITALAN
Jabatan Teknologi Maklumat dan Pengurusan Ilmu
Unit Penyelenggaraan Sistem
Menyediakan Live Streaming untuk program KPT Pace pada 20-21 Jun 2022 dan 23 Jun 2022.
Penambahbaikan modul semakan yuran sistem PUPW/ e-Finance bagi invoicing/ receipt untuk pelajar baharu dan pelajar kanan. Dijangka siap hujung bulan Jun 2022.
Pembangunan Sistem Lecturer Claim dijangka bermula pada July 2022

## Slide 4
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
JAN
FEB
MAR
APR
DEC
JUL
AUG
SEPT
OCT
MAY
JUN
NOV
PERIOD
TASKS
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
SISTEM APEL
Modul Admission
Modul Penilaian
1 BULAN
2 BULAN
1 BULAN
2 BULAN
Modul Aptitude Test
JAN
FEB
MAR
APR
DEC
JUL
AUG
SEPT
OCT
MAY
JUN
NOV
PERIOD
TASKS
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
SISTEM RPEL
Modul Admission
Modul Penilaian
Modul Aptitude Test
1 BULAN
2 BULAN
2 BULAN
1 BULAN
Maintenance
Modul Aduan
Maintenance
1 BULAN
Milestone : System development continued from other staff
Penambahbaikan berdasarkan maklumbalas MQA
PERANCANGAN APEL & RPEL

## Slide 5
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
JAN
FEB
MAR
APR
DEC
JUL
AUG
SEPT
OCT
MAY
JUN
NOV
PERIOD
TASKS
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
SISTEM ADMISSION PUPW
Pembangunan baharu
Modul Kemasukan
Modul Semakan Yuran
1 BULAN
3 Bulan
1 minggu
PERANCANGAN ADMISSION PUPW
Modul Saringan
3 Bulan

## Slide 6
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
JAN
FEB
MAR
APR
DEC
JUL
AUG
SEPT
OCT
MAY
JUN
NOV
PERIOD
TASKS
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
SISTEM E-FINANCE
Maintenance
12 BULAN
Invoicing/ Receipt
ePRF
PERANCANGAN E-FINANCE
Penambahbaikan berdasarkan pembangunan sistem baharu

## Slide 7
UMP ADVANCED | umpadvanced.ump.edu.my
EDUCATION FOR ALL, NO ONE LEFT BEHIND
JAN
FEB
MAR
APR
DEC
JUL
AUG
SEPT
OCT
MAY
JUN
NOV
PERIOD
TASKS
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
SISTEM CLAIM
Development
2 BULAN
Modul Pendaftaran
Modul Claim
PERANCANGAN LECTURER CLAIM